## Sheet1
User story id | User story name | User story step defination | Assigned to | Estimated time | Actual time | Acceptance Criteria | Status | Remarks
User001 | Login and Search for Hotels | As a Traveler, I want to login search for hotels. | Hitesh | 3 hours | 3 hours | Search results include hotels matching the destination | Complete | NA
User002 | Find Available Options | As a Traveler, I want to find available options for my hotel | Kumar jd | 1 hour | 1 hour | The system shall allow users to filter search results by categories. | Not started | NA
User003 | View Hotel Details | As a Traveler , I want to view detailed information about each hotel, | Jaswanth | 4 hour | 4 hour | display key information like hotel name, photos, price, | Progress | NA
User004 | Feedback | As a Traveler, I want to view including photos, amenities, and reviews | Apurva shinde | 7 hour | 4 hour | The system shall include photos, amenities, and user reviews in the hotel details. | Complete | NA
User005 | Select Catagorie | As a Traveler, I want to Select the catagories . | Amar kohle | 5 hour | 3 hour | The system shall allow users to filter search results by categories | Progress | NA
User006 | Select Date | As a Traveler, I want to Select the date. | Anusha Bharath | 1 hour | 1 hour | he user shall be able to enter check-in and check-out dates. | Complete | NA
User007 | Book Room | As a Traveler, I want to book the room. | Bhavani | 4 hour | 3 hour | The system shall allow users to select and book a room | Progress | NA
User007 | Transition Management | As a Traveler, I want to payment option. | Atin | 5 hour | 4 hour | The system shall provide a secure payment process during booking. | Complete | NA
User007 | Notify About Booking | As a Traveler, I want to notify about booking . | Ashish | 4 hour | 3 hour | The system shall notify users with booking details upon successful booking | Progress | NA
User008 | Confirm Room Booking | As a Traveler, I want to confirm my room booking. | Aravind Naidu | 3 hour | 2 hour | The system shall display a confirmation screen for users to confirm or cancel the booking | Progress | NA
User009 | Logout | As a Traveler, I want to logout . |  | 3 hour | 2 hour | The system shall securely log out users and redirect them to the homepage or login screen. | Complete | NA